## Chart
Task / Days from Project Start

## Data
		All	Dan	Charlie	Steve	Mark	Martin	Ashley	Kenny	Kieran	Android-Dev	Web-Dev
Final Report	80				9	28
Documentation Deadline	103	17

Testing	92					4				4
Web Programming	61											31
Android Programming	61										31
Delivery Of Complete Software	61	42

Testing	58					2
Web Programming	20											38
Android Programming	20										38
1st Working Prototype	54	7

Detailed Design	33										8	8
Interface Description	33										8	8
Dependency Description	33										8	8
Decomposition Description	33										8	8
Introduction	33									16
Design Specification	33	21

2nd ½	12					17
1st ½	12						17
Test Specification	26	7

Risk Analysis	0					23
Gantt Chart	0		23
Web UI Design	0				24
Android UI Design	0							19
Web Use-Cases	0				22
Android Use-Cases	0			22
Overview of Proposed System	0						23
Introduction	0								23
Project Plan	0	26

Group Project	0	120