## Chart
Task / Days from Project Start

## Data
		All	Dan	Charlie	Steve	Mark	Martin	Ashley	Kenny	Kieran	Android-Dev	Web-Dev
Group Project	0	120
Documentation Deadline	103	17
Final Report	80				9	28

Delivery Of Complete Software	61	42
Testing	92					4				4
Web Programming	61											31
Android Programming	61										31

1st Working Prototype	54	7
Testing	58					2
Web Programming	20											38
Android Programming	20										38

Design Specification	33	21
Detailed Design	33										8	8
Interface Description	33										8	8
Dependency Description	33										8	8
Decomposition Description	33										8	8
Introduction	33									16

Test Specification	26	7
2nd ½	12					17
1st ½	12						17

Project Plan	0	26
Risk Analysis	0					23
Gantt Chart	0		23
Web UI Design	0				24
Android UI Design	0							19
Web Use-Cases	0				22
Android Use-Cases	0			22
Overview of Proposed System	0						23
Introduction	0								23