## Data
		All	Dan	Charlie	Steve	Mark	Martin	Ashley	Kenny	Kieran	Android-Dev	Web-Dev
Group Project	0	120

Project Plan	0	26
Introduction	0								23
Overview of Proposed System	0								23
Android Use-Cases	0			22
Web Use-Cases	0				22
Android UI Design	0							19
Web UI Design	0				24
Gantt Chart	0		23
Risk Analysis	0					23

Test Specification	26	7
1st ½	12						17
2nd ½	12					17

Design Specification	33	21
Introduction	33									16
Decomposition Description	33										8	8
Dependency Description	33										8	8
Interface Description	33										8	8
Detailed Design	33										8	8

1st Working Prototype	54	7
Android Programming	20										38
Web Programming	20											38

Delivery Of Complete Software	61	42
Android Programming	61										39
Web Programming	61											39

Documentation Deadline	103	17
Final Report	80				9	28